## Tickets
ID | Summary | Status | Assignee | Custom Field 27101 | Issue Type | Resolution Date | Custom Field 10704
ABLCTR-370 | PVS Consultation | Closed | Sisk, Brian |  | Task | 2025-10-31T11:44:13.000-0500
ABLCTR-369 | PVS Planning | Closed | Sisk, Brian |  | Task | 2025-10-31T11:39:16.000-0500
ABLCTR-363 | Functional Testing | Closed | Martin, Reuben |  | Sub-task | 2025-10-28T13:50:38.000-0500
ABLCTR-357 | Duplicate, Ignore | Closed |  |  | Sub-task | 2025-10-22T10:41:58.000-0500
ABLCTR-356 | Prep Work | Closed | Martin, Reuben |  | Sub-task | 2025-10-28T13:32:17.000-0500
ABLCTR-352 | Abldev1 linux system updates | Issue Done | Martin, Reuben |  | Task | 2025-10-29T10:44:35.000-0500
ABLCTR-351 | [ABLSCALE1] - Capture Baselines. | Closed | M, Mangalnath |  | Sub-task | 2025-10-23T01:11:54.000-0500
ABLCTR-350 | [ABLSCALE1] - Install Packages | Closed | M, Mangalnath |  | Sub-task | 2025-10-23T01:09:58.000-0500
ABLCTR-346 | [ABLSCALE1] - Capture Baselines. | Closed | M, Mangalnath |  | Sub-task | 2025-10-23T01:06:50.000-0500
ABLCTR-345 | [ABLSCALE1] - Install Packages | Closed | M, Mangalnath |  | Sub-task | 2025-10-23T01:05:34.000-0500
ABLCTR-344 | [ABLSCALE1] - 2025.4.01 TP02 Millennium Innovation Release Testing for 33 workflows | Closed | M, Mangalnath |  | Task | 2025-10-23T01:07:29.000-0500
ABLCTR-342 | CAMM7 Chef-System-Patching Performance Testing | Closed | Martin, Reuben |  | Story | 2025-10-28T13:50:49.000-0500
ABLCTR-327 | Fed Monthly Nov Release Testing | Closed | Cackler, Ian |  | Task | 2025-11-03T11:00:37.000-0600
ABLCTR-264 | [ABLSCALE3] - 2025.4.01 ST6 Millennium Innovation Release Testing for 33 workflows | Closed | Tripathi, Aayush |  | Task | 2025-10-23T00:37:37.000-0500
ABLCTR-263 | [ABLSCALE1] - 2025.4.01 TP01 Millennium Innovation Release Testing for 33 workflows | Closed | M, Mangalnath |  | Task | 2025-10-23T00:55:56.000-0500
ABLCTR-258 | [ABLSCALE3] - 2025.4.01 ST5 Millennium Innovation Release Testing for 33 workflows | Closed | Tripathi, Aayush |  | Task | 2025-10-23T00:37:21.000-0500
ABLCTR-249 | [ABLSCALE3] - 2025.4.01 ST4 Millennium Innovation Release Testing for 33 workflows | Closed | Tripathi, Aayush |  | Task | 2025-10-23T00:37:15.000-0500
ABLCTR-244 | WLS 14 Migration ¦ Abilities environment on OCI | Closed | Baldanza, Brandon |  | Task | 2025-11-05T10:38:58.000-0600
ABLCTR-120 | AblTestReq - Test impact of Extended Statistics on execution plans and performance | Closed | Baldanza, Brandon |  | Task | 2025-10-22T09:43:58.000-0500
ABLCTR-9 | TLS Support for MQ | Closed | Hapner, Max |  | Task | 2025-11-10T13:44:26.000-0600