## Tickets
ID | Summary | Root Cause | Toolkit Version | Viewer Version | Issue Type | Defect Jira | Ticket Priority | Waiting Time | Investigation Effort | Assignee | Current Status | Ageing | Next Action Item | Comments | Date Created | Date Resolved | Linked Issues
DTVIEWER-19980 | HAMC_QAT: MySQL corruption due to improper device shutdowns. | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 6.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-11-28T12:23:44.000-0600
DTVIEWER-19979 | Resulted MRSA not pulling into Microbiology results on the viewer | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 6.0 days | null | Singhal, Avneesh | Investigation | null | null | null | 2025-11-28T09:33:18.000-0600
DTVIEWER-19978 | In case of Stand-alone PC load, VPUMP is always getting started as BEGIN NOW | null | N/A | N/A | Sub-task | Medium |  |  | null | Datta, Saikat | In Progress | null | null | null | 2025-11-28T06:37:46.000-0600
DTVIEWER-19977 | Errors creating credential store gg_credentialstore.py | null | N/A | 724Access Downtime Viewer 5.13.1 | Issue Investigation | Medium |  | 7.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-11-27T09:43:19.000-0600
DTVIEWER-19976 | WARNING: Unable to determine password for ... user | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 6.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-27T02:35:01.000-0600 | 2025-12-05T05:13:29.000-0600 | DTVIEWER-19685
DTVIEWER-19975 | Unable to successfully pull audits from the following devices | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 7.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-11-27T02:24:37.000-0600
DTVIEWER-19974 | 462483147 NRTH_GA needs CSN, Partial Log and trail file fixes applied | null | N/A | 724Access Downtime Viewer 5.16 | Issue Investigation | Medium |  | 8.0 days | null | Singhal, Avneesh | Waiting for Reporter Input | null | null | null | 2025-11-26T14:57:30.000-0600
DTVIEWER-19973 | Package Access Request for 673494 from BAYC_FL | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 3.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-11-26T13:51:09.000-0600 | 2025-12-01T16:14:10.000-0600
DTVIEWER-19972 | Viewer repository unification | null | N/A | N/A | Feature | Medium |  |  | null | Lau, Sandy | Submitted | null | null | null | 2025-11-26T11:33:20.000-0600 |  | DTVIEWER-20007, DTVIEWER-20008, DTVIEWER-20010
DTVIEWER-19971 | CHSI_TN Unable to determine password for root user | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | High |  | 3.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-26T10:57:07.000-0600 | 2025-12-01T23:21:43.000-0600
DTVIEWER-19970 | fix unit test dtv | null | N/A | N/A | Task | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-26T10:10:18.000-0600
DTVIEWER-19969 | 462305991 CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkit in PROD | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 8.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-26T08:48:48.000-0600
DTVIEWER-19968 | address amb vulnerability | null | N/A | N/A | Task | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-26T07:55:41.000-0600
DTVIEWER-19967 | address dtv vulnerability | null | N/A | N/A | Task | Medium |  |  | null | Costa, Floid | In Progress | null | null | null | 2025-11-26T07:54:38.000-0600
DTVIEWER-19966 | Inconsistent GGSERR.LOG Filesize Value across the codebase | null | N/A | 724Access Downtime Viewer 5.20 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-26T06:01:37.000-0600 |  | DTVIEWER-19931
DTVIEWER-19965 | 462673434 LRMC_FL SSH Issues on 2025.01 and 5.17 | null | 724Access Replication Management 2025.01 | N/A | Issue Investigation | High |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-26T00:08:51.000-0600 | 2025-11-26T11:29:57.000-0600
DTVIEWER-19964 | Validating PCLADB and CERN_724ADM grants at the time of MT SETUP and UPGRADE | null | N/A | N/A | Story | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-25T23:58:57.000-0600
DTVIEWER-19963 | 724 Replication Management 2025.02.03 Certification | null | N/A | N/A | Feature | Medium |  |  | null | Lau, Sandy | Open | null | null | null | 2025-11-25T15:14:55.000-0600
DTVIEWER-19962 | Obligation for 1-000000552436 - 724Access Downtime Viewer 5.19 | null | N/A | N/A | Obligation | Medium |  |  | null | SM, Lakshmi | Pending Approval | null | null | null | 2025-11-25T08:28:25.000-0600
DTVIEWER-19961 | SR 462641999 HUNT_AL Can't See 724 in Lights On. Olympus works fine. | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | Medium |  | 9.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-25T08:22:01.000-0600
DTVIEWER-19960 | REGM_IA - Home Medications and Problem List in PROD does not match 724 | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | Medium |  | 10.0 days | null | Bhansali, Pranjal | Waiting for Reporter Input | null | null | null | 2025-11-24T15:37:16.000-0600
DTVIEWER-19959 | TK 2025.04 sarail72403 mt_setup throws an error | null | 724Access Replication Management 2025.04 | N/A | Issue Investigation | Medium |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-24T11:48:21.000-0600 | 2025-11-24T14:56:17.000-0600
DTVIEWER-19958 | mt_setup script is not creating the required grants for role role_cern_724adm | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | Critical |  | 3.0 days | null | Datta, Saikat | Closed | null | null | null | 2025-11-24T06:38:02.000-0600 | 2025-11-28T06:33:26.000-0600
DTVIEWER-19957 | MDCH_AE: Vrep process abended with Incompatible record error | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | Medium |  | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T12:43:43.000-0600 | 2025-12-04T08:34:14.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19956 | MDCH_AE: Multiple vpumps are abended with Unexpected LOB record error | null | 724Access Replication Management 2024.02.OCI | N/A | Issue Investigation | Medium |  | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T12:38:20.000-0600 | 2025-12-04T08:34:37.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19955 | MHG_MS 462541668 Unable to open modify tab in Admin Tool | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 11.0 days | null | Bhansali, Pranjal | Waiting for Reporter Input | null | null | null | 2025-11-21T11:53:01.000-0600
DTVIEWER-19954 | TSSO_CD - Failing MT_SETUP FAILINIG at DB LINK test | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | High |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T10:42:42.000-0600 | 2025-11-21T14:33:44.000-0600 | DTVIEWER-19413
DTVIEWER-19953 | AHSW_CA source monitoring not working | null | N/A | N/A | Task | Medium |  |  | null | Sun, Chloe | Closed | null | null | null | 2025-11-21T09:50:41.000-0600 | 2025-11-21T10:16:13.000-0600
DTVIEWER-19952 | No DTCAP row found in secondary MT in d7a_gg_process table | null | N/A | 724Access Downtime Viewer 5.18.1 | Task | Medium |  |  | null | Botta, Venkata Satya Prasanth Kumar | Closed | null | null | null | 2025-11-21T06:12:59.000-0600 | 2025-11-21T13:26:49.000-0600 | DTVIEWER-19948
DTVIEWER-19951 | WCAG 1.4.13 Content on Hover or Focus | null | N/A | 724Access Ambulatory Viewer 1.4 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-20T17:00:55.000-0600
DTVIEWER-19950 | Related persons not displaying within 724 patient record | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 12.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-20T05:03:38.000-0600
DTVIEWER-19949 | Issues while setting up monitoring jar giving exception | null | 724Access Replication Management 2025.02.02 | N/A | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-20T03:36:47.000-0600 | 2025-11-21T01:24:22.000-0600
DTVIEWER-19948 | DTV-VR-GoldenGate Stats Monitoring issue with -gs -H | null | N/A | 724Access Downtime Viewer 5.18.1 | Task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-20T01:41:05.000-0600 | 2025-11-21T01:23:19.000-0600 | DTVIEWER-19952
DTVIEWER-19947 | Modify DR_MENU Option to Upgrade MySQL Enterprise Edition | null | N/A | N/A | Sub-task | Medium |  |  | null | Singla, Rahul | In Progress | null | null | null | 2025-11-19T23:11:45.000-0600 |  | DTVIEWER-19944
DTVIEWER-19946 | Device Loads w/ Latest MySQL Enterprise Edition (8.0.43) | null | N/A | N/A | Sub-task | Medium |  |  | null | Dhingra, Gaurav | Open | null | null | null | 2025-11-19T23:09:48.000-0600 |  | DTVIEWER-19945
DTVIEWER-19945 | Device Loads w/ Latest MySQL Community Edition (8.0.43 or later) | null | N/A | N/A | Sub-task | Medium |  |  | null | Dhingra, Gaurav | Open | null | null | null | 2025-11-19T23:08:15.000-0600 |  | DTVIEWER-19944, DTVIEWER-19946
DTVIEWER-19944 | Modify DR_MENU Option to Upgrade MySQL Community Edition | null | N/A | N/A | Sub-task | Medium |  |  | null | Singla, Rahul | In Progress | null | null | null | 2025-11-19T23:03:48.000-0600 |  | DTVIEWER-19273, DTVIEWER-19945, DTVIEWER-19947
DTVIEWER-19943 | 462388422 CHS_TN Need Assistance with 5.17 upgrade. SSH not functioning | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | High |  | 1.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-19T22:58:09.000-0600 | 2025-11-20T23:42:46.000-0600
DTVIEWER-19942 | Display Document Name first in DTV | null | N/A | N/A | Story | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-19T16:40:24.000-0600 |  | DTVIEWER-19918
DTVIEWER-19941 | Unable to install CertService during ambulatory load when card option is selected | null | N/A | N/A | Task | Medium |  |  | null | Uppalapati, Nandita | Closed | null | null | null | 2025-11-19T12:13:29.000-0600 | 2025-11-19T12:14:31.000-0600
DTVIEWER-19940 | GLAS_KY Pumper load error 'subprocess' is not defined. Did you forget to import 'subprocess'? | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | Critical |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-19T10:33:12.000-0600 | 2025-11-20T09:47:42.000-0600
DTVIEWER-19939 | 724Access Printing Blank Medication Orders Only - Translation Changes | null | N/A | N/A | Story | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-19T10:18:45.000-0600 | 2025-12-02T21:44:09.000-0600 | DTVIEWER-18657, DTVIEWER-18591
DTVIEWER-19938 | Local Admin Check Fails Due to Orphaned/Ghost Sids in Admin Group | null | 724Access Replication Management 2024.04.04 | N/A | Issue Investigation | Medium |  | 4.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-19T10:13:39.000-0600 | 2025-11-25T15:57:55.000-0600
DTVIEWER-19937 | Refine and Test Script | null | N/A | N/A | Sub-task | Medium |  |  | null | Burgstahler, Aiden | In Progress | null | null | null | 2025-11-19T09:41:01.000-0600
DTVIEWER-19936 | Added Provider values not displayed in the Firstnet Patient list grid | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-19T08:36:51.000-0600 | 2025-11-20T04:13:50.000-0600
DTVIEWER-19935 | DTV-VR-Viewer-PowerPlans - Issues | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null |  | Closed | null | null | null | 2025-11-19T01:27:09.000-0600 | 2025-12-04T09:28:04.000-0600 | DTVIEWER-20004
DTVIEWER-19934 | reduce build size remove existing libs from tk packaging | null | N/A | N/A | Task | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-19T01:25:43.000-0600
DTVIEWER-19933 | VIN trail file Naming convention to be 6 digits | null | N/A | N/A | Sub-task | Medium |  |  | null | Datta, Saikat | In Progress | null | null | null | 2025-11-19T00:51:07.000-0600
DTVIEWER-19932 | Facility Pump - Child PC load for GG Microservice | null | N/A | N/A | Sub-task | Medium |  |  | null | Datta, Saikat | In Progress | null | null | null | 2025-11-19T00:48:17.000-0600
DTVIEWER-19931 | GGSERR.LOG Filesize Correct Value | null | 724Access Replication Management 2024.04.04 | N/A | Issue Investigation | Medium |  | 5.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-18T16:36:57.000-0600 | 2025-11-26T06:06:44.000-0600 | DTVIEWER-18977, DTVIEWER-19966
DTVIEWER-19930 | Filter orders on viewer using event set | null | N/A | N/A | Story | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-18T10:59:36.000-0600 |  | DTVIEWER-19217
DTVIEWER-19929 | Missing NED's on the viewer if documents are not valid | null | N/A | 724Access Ambulatory Viewer 1.3 | Defect | Medium |  |  | null |  | Open | null | null | null | 2025-11-18T10:23:37.000-0600 |  | DTVIEWER-19220, DTVIEWER-19814
DTVIEWER-19928 | Lab Collection Search - Issues | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-18T07:46:50.000-0600 | 2025-12-04T09:28:05.000-0600 | DTVIEWER-20003
DTVIEWER-19927 | Enhancement to Improve visibility of unverified orders | null | N/A | 724Access Downtime Viewer 5.15.3 | Story | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-18T04:12:47.000-0600 |  | DTVIEWER-19881
DTVIEWER-19926 | Clarifications/concerns during non-prod testing (5.16.2) | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 14.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-18T02:33:07.000-0600
DTVIEWER-19925 | Add FirstNet patient not showing providers | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-18T00:31:16.000-0600 | 2025-11-18T00:37:23.000-0600
DTVIEWER-19924 | The print section of microbiology viewer | null | N/A | N/A | Task | Medium |  |  | null | Kumari, Maneesha | Closed | null | null | null | 2025-11-18T00:27:17.000-0600 | 2025-12-04T09:02:49.000-0600
DTVIEWER-19923 | Update the wiki page ¦ 724 VG for GG and Toolkit Files in mid-tiers | null | N/A | N/A | Task | Medium |  |  | null | Patel, Sameena | In Progress | null | null | null | 2025-11-17T23:34:45.000-0600
DTVIEWER-19922 | address toolkit vulnerability | null | N/A | N/A | Task | Medium |  |  | null | Costa, Floid | Validating Issue | null | null | null | 2025-11-17T23:30:33.000-0600
DTVIEWER-19921 | Add Search Bar for Non-expiring Documents View | null | N/A | N/A | Story | Medium |  |  | null |  | Open | null | null | null | 2025-11-17T13:48:52.000-0600 |  | DTVIEWER-19914
DTVIEWER-19920 | Support multitenant configuration for pc_daily_report | null | N/A | N/A | Story | Medium |  |  | null |  | Open | null | null | null | 2025-11-17T13:37:50.000-0600 |  | DTVIEWER-19862
DTVIEWER-19919 | AMB PC Load Failure Due to Incorrect Folder Path for Cert Service | null | N/A | 724Access Ambulatory Viewer 1.4.OCI | Defect | Critical |  |  | null | Uppalapati, Nandita | Closed | null | null | null | 2025-11-17T12:16:57.000-0600 | 2025-11-19T12:12:10.000-0600
DTVIEWER-19918 | HAMC_QAT: Document Display | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 2.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-17T11:07:50.000-0600 | 2025-11-19T16:42:32.000-0600 | DTVIEWER-19942
DTVIEWER-19917 | BE_UPGRADE Failed due to failure in copying ENCKEYS to Midtier | null | 724Access Replication Management 2025.04 | N/A | Spike | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-17T04:59:02.000-0600
DTVIEWER-19916 | u01 directory full on WSH724103 and MTPUMP on MT is abended. | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 15.0 days | null | Gaskell, Robin | Submitted | null | null | null | 2025-11-17T04:50:17.000-0600
DTVIEWER-19915 | Purge is not happening in Downtime data maintenance VR (intermittently) | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Low |  |  | null | Botta, Venkata Satya Prasanth Kumar | Closed | null | null | null | 2025-11-17T02:20:35.000-0600 | 2025-12-04T09:30:17.000-0600 | DTVIEWER-20002
DTVIEWER-19914 | Non-Expiring Document Tab in Global Prefs Search Bar Enhancement | null | N/A | 724Access Downtime Viewer - None | Issue Investigation | Medium |  | 1.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-14T10:26:05.000-0600 | 2025-11-17T13:50:57.000-0600 | DTVIEWER-19921
DTVIEWER-19913 | [Existing] Encounter class exclusion removes records for matching encounter type, but encounter class data still appears in viewer | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-14T10:20:50.000-0600 | 2025-11-21T11:13:20.000-0600
DTVIEWER-19912 | UNZA - intermittent SSH issues from Midtier to Workstation | null | N/A | 724Access Downtime Viewer 5.16.3 | Issue Investigation | Medium |  | 16.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-14T03:45:47.000-0600
DTVIEWER-19911 | Passwords not working post toolkit upgrade | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | Medium |  | 15.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-13T20:33:42.000-0600 | 2025-12-05T08:06:44.000-0600 | DTVIEWER-19985
DTVIEWER-19910 | SMRC_QAT: JSON return value is not valid error during the reverse ssh | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | Medium |  | 17.0 days | null | Bhansali, Pranjal | Waiting for Reporter Input | null | null | null | 2025-11-13T11:35:36.000-0600
DTVIEWER-19909 | DNAR Status not visible on DTV patient demographic banner unless you hover over it | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 7.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-13T09:18:44.000-0600 | 2025-11-24T13:38:16.000-0600
DTVIEWER-19908 | TK 2025.02.01 dr_kart_info.ksh needs to be fixed as its looking at the local ORACLE_HOME to connect instead of the remote ORACLE_HOME | null | N/A | 724Access Replication Managemen 2025.02.01 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-13T09:09:13.000-0600
DTVIEWER-19907 | Patient list mismatch between Millennium and 724 DTV | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 5.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-13T03:40:32.000-0600 | 2025-11-20T10:43:16.000-0600
DTVIEWER-19906 | KING_AE: Multiple dtv load failures with Errors comparing table lists between parameter and report files | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | High |  | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-13T00:49:44.000-0600 | 2025-12-08T05:48:53.000-0600
DTVIEWER-19905 | JDAM_GA -VPUMP Abended | null | N/A | 724Access Ambulatory Viewer 1.3.1 | Issue Investigation | Medium |  | 1.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-12T19:03:40.000-0600 | 2025-11-14T15:11:25.000-0600 | DTVIEWER-18232, DTVIEWER-18379
DTVIEWER-19904 | ORHO_OK Allergy Reaction Information Not Crossing Over | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | High |  | 18.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-12T16:05:14.000-0600
DTVIEWER-19903 | Validate where Crowdstrike is logging the user and exposing password | null | N/A | N/A | Spike | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-12T11:53:57.000-0600
DTVIEWER-19902 | Crowdstrike flagging SvcD7A user and exposing password | null | N/A | N/A | Feature | Medium | DTVIEWER-19040 |  | null | Balasubramanian, Vignesh | Submitted | null | null | null | 2025-11-12T11:50:54.000-0600 |  | DTVIEWER-17329
DTVIEWER-19901 | DUBO_PA - Requesting access for Package 656378 -5.15.2 724 DTV | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | Medium |  | 0.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-11-12T11:46:44.000-0600 | 2025-11-12T14:42:10.000-0600
DTVIEWER-19900 | Token Not Generated When Logging in Immediately After Closing Application | null | N/A | N/A | Spike | Medium | DTVIEWER-19801 |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-12T10:29:25.000-0600 | 2025-11-13T21:44:15.000-0600
DTVIEWER-19899 | 462540091 CPTL_NH LOB, CSN, Trailfile fixes needed | null | 724Access Replication Management 2024.04.03 | N/A | Issue Investigation | Medium |  | 0.0 days | null | Gaskell, Robin | Closed | null | null | null | 2025-11-12T10:22:03.000-0600 | 2025-11-12T10:59:27.000-0600
DTVIEWER-19898 | MT Purge is not running for 724 OCI clients | null | N/A | N/A | Task | High |  |  | null |  | Submitted | null | null | null | 2025-11-12T09:32:49.000-0600
DTVIEWER-19897 | KING_AE: Not able to install the DTV | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | Medium |  | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-12T06:10:01.000-0600 | 2025-12-08T05:47:35.000-0600
DTVIEWER-19896 | 15-char password validations not working in OCI properly | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-12T04:00:08.000-0600 | 2025-11-19T00:28:10.000-0600
DTVIEWER-19895 | 724monitoring jar is not working in source and midtier VM | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-12T02:10:27.000-0600 | 2025-11-14T09:53:43.000-0600
DTVIEWER-19894 | SSO - Card Logon page displayed empty | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-11T06:03:21.000-0600 | 2025-11-12T09:20:54.000-0600
DTVIEWER-19893 | Unable to view documents in the doc viewer for some documents | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | High |  |  | null | Adhikari, Tamal | Closed | null | null | null | 2025-11-11T01:26:52.000-0600 | 2025-11-12T01:39:35.000-0600
DTVIEWER-19892 | LCOX_MO - Issues installing Cygwin | null | N/A | 724Access Downtime Viewer 5.15 | Issue Investigation | Medium |  | 20.0 days | null | Bhansali, Pranjal | Waiting for Reporter Input | null | null | null | 2025-11-10T15:27:32.000-0600
DTVIEWER-19891 | CHR_NY Pre-Admit encounter on their Downtime Census, its not active encounter | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 20.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-10T14:19:38.000-0600
DTVIEWER-19890 | CDDN_UK 5.17/25.01 needs pc_find_next_rba and dtv clean up scrips fixed. | null | N/A | 724Access Downtime Viewer 5.17 | Issue Investigation | High |  | 1.0 days | null | Gaskell, Robin | Closed | null | null | null | 2025-11-10T10:30:50.000-0600 | 2025-11-11T10:40:47.000-0600
DTVIEWER-19889 | NBHS_CA, Data load Failure - VLOAD03 Fails due to Database error 1264. | null | N/A | 724Access Downtime Viewer - None | Issue Investigation | Medium |  | 20.0 days | null | Sun, Chloe | Waiting for Reporter Input | null | null | null | 2025-11-10T07:31:04.000-0600
DTVIEWER-19888 | File -> View collected audits not working | null | N/A | 724Access Downtime Viewer 5.18.1 | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-10T06:30:29.000-0600 | 2025-11-10T23:28:34.000-0600
DTVIEWER-19887 | CERN_EMPL Apply 2024.02.01.OCI Tookit fixes to the domain | null | 724Access Replication Management - None | N/A | Task | High |  |  | null | Sun, Chloe | Submitted | null | null | null | 2025-11-10T02:06:12.000-0600 |  | DTVIEWER-19872
DTVIEWER-19886 | Accept button not working in Viewer Acknowledge window | null | N/A | N/A | Sub-task | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-09T22:56:39.000-0600 | 2025-11-17T09:41:50.000-0600
DTVIEWER-19885 | HUNT_AL - mysql innodb corruption issue | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | Medium |  | 20.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-07T18:06:01.000-0600 | 2025-12-08T05:07:21.000-0600
DTVIEWER-19884 | Fix MT_SETUP failure when run after MT_UPGRADE | null | 724Access Replication Management - None | N/A | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-07T17:02:56.000-0600 |  | DTVIEWER-19883
DTVIEWER-19883 | MT_SETUP Failure on Existing Midtier during Rebuild | null | 724Access Replication Management - None | N/A | Issue Investigation | Medium |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-07T16:25:42.000-0600 | 2025-11-07T17:05:07.000-0600 | DTVIEWER-19884
DTVIEWER-19882 | Need Assistance troubleshooting KMC_HI Admin tool | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | Medium |  | 21.0 days | null | Thakrar, Mihir | Waiting for Reporter Input | null | null | null | 2025-11-07T12:31:58.000-0600
DTVIEWER-19881 | Enhancement to Improve visibility of unverified orders | null | N/A | 724Access Downtime Viewer 5.15.3 | Issue Investigation | Medium |  | 6.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-07T12:20:52.000-0600 | 2025-11-18T06:46:27.000-0600 | DTVIEWER-19927
DTVIEWER-19880 | pc_daily_report.ksh failing when multiple contact details added for a facility pump | null | 724Access Replication Management - None | N/A | Defect | Medium |  |  | null |  | Open | null | null | null | 2025-11-07T08:43:42.000-0600 |  | DTVIEWER-19862
DTVIEWER-19879 | FAIR_AK, Confusion regarding DTV password requirement. | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-07T07:03:33.000-0600 | 2025-11-07T08:50:34.000-0600 | DTVIEWER-18927
DTVIEWER-19878 | openSSH installation failing | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 7.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-07T06:13:26.000-0600 | 2025-11-18T08:14:46.000-0600
DTVIEWER-19877 | Non expiring Documents are not showing in the viewer | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | High |  |  | null | Adhikari, Tamal | Closed | null | null | null | 2025-11-07T03:14:38.000-0600 | 2025-11-19T08:25:13.000-0600
DTVIEWER-19876 | Removing SITHS card from 724DTV does not logout user | null | N/A | 724Access Downtime Viewer 5.16.3 | Spike | High |  |  | null | Uppalapati, Nandita | Open | null | null | null | 2025-11-07T01:41:22.000-0600 |  | DTVIEWER-19844
DTVIEWER-19875 | VGR - Unable to SSH from Source to MT | null | N/A | 724Access Downtime Viewer 5.18.1 | Issue Investigation | Medium |  | 17.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-06T14:29:55.000-0600 | 2025-12-01T23:50:58.000-0600
DTVIEWER-19874 | DTV load Failing | null | N/A | 724Access Downtime Viewer - None | Issue Investigation | Medium |  | 8.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-06T11:02:35.000-0600 | 2025-11-19T10:20:00.000-0600
DTVIEWER-19873 | Logging not working for security utils library | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | High |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-06T10:02:11.000-0600 | 2025-11-10T09:30:01.000-0600
DTVIEWER-19872 | CCH_CD Apply fixes to environment | null | 724Access Replication Management - None | N/A | Issue Investigation | Medium |  | 7.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-06T09:57:35.000-0600 | 2025-11-17T15:34:51.000-0600 | DTVIEWER-19887
DTVIEWER-19871 | SR 462341708 LCAH_NCR DTV install failing to connect to database | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | Medium |  | 11.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-06T08:42:51.000-0600 | 2025-11-21T14:31:33.000-0600
DTVIEWER-19870 | USC_CA Admin Tool and DTV Load Issues | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 1.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-06T08:15:31.000-0600 | 2025-11-07T13:07:59.000-0600
DTVIEWER-19869 | NAH_AZ: Admin Tool Installation Issues | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 0.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-06T08:05:59.000-0600 | 2025-11-06T08:09:10.000-0600
DTVIEWER-19868 | Modifying the Toolkit Reference Wiki Pages for creating GG and C##GGADMIN DB Users | null | 724Access Replication Management 2025.04 | N/A | Story | Medium |  |  | null | Botta, Venkata Satya Prasanth Kumar | Submitted | null | null | null | 2025-11-06T01:39:54.000-0600 |  | DTVIEWER-19857, DTVIEWER-19819
DTVIEWER-19867 | 406 Error Due to Unexpected Accept: application/json Header in Auth API | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-05T23:23:38.000-0600 | 2025-11-06T09:19:06.000-0600
DTVIEWER-19866 | 406 Error Due to Unexpected Accept: application/json Header in Auth API | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-05T23:20:52.000-0600 | 2025-11-05T23:25:10.000-0600
DTVIEWER-19865 | VLOAD01 Fails Due to CE_DYNAMIC_LABEL_ID Incorrect Value | null | 724Access Replication Management 2025.04 | N/A | Issue Investigation | Medium |  | 4.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-11-05T16:10:05.000-0600 | 2025-11-12T12:44:18.000-0600
DTVIEWER-19864 | 462641030 KTCH_CD Package Access Request 667795 | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | Medium |  | 23.0 days | null | Patel, Sameena | Waiting for Reporter Input | null | null | null | 2025-11-05T14:52:41.000-0600
DTVIEWER-19863 | mt_setup_stats needs to push schema stats if not configured | null | 724Access Replication Management 2025.02.02 | N/A | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-05T12:18:30.000-0600 |  | DTVIEWER-19793
DTVIEWER-19862 | CERN_COMC MidTier Alerting Emails | null | N/A | 724Access Downtime Viewer 5.15.OCI | Issue Investigation | Medium |  | 14.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-05T12:16:52.000-0600 | 2025-11-26T08:17:24.000-0600 | DTVIEWER-19529, DTVIEWER-19920, DTVIEWER-19880
DTVIEWER-19861 | LEWIS_UK - 724 DTV Printing Preference Issue (Build: 2022.03) | null | 724Access Replication Management 2024.04.03 | N/A | Issue Investigation | Medium |  | 5.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-05T11:58:21.000-0600 | 2025-11-13T03:36:25.000-0600
DTVIEWER-19860 | DEPH_MA full OCI setup, TK 2024.02.01.OCI BE_SETUP.ksh throwing an error | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 11.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-05T11:36:18.000-0600 | 2025-11-20T23:40:27.000-0600
DTVIEWER-19859 | Patient with no encounter still showing clinical data after running report downloader jar | null | 724Access Replication Management 2025.02.02 | N/A | Defect | Medium |  |  | null | Adhikari, Tamal | Closed | null | null | null | 2025-11-05T07:11:31.000-0600 | 2025-11-12T01:45:52.000-0600
DTVIEWER-19858 | Collect audit file menu is erroring out in case of site admins | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | Medium |  |  | null | Nagaraju, Priyanka | Closed | null | null | null | 2025-11-05T04:31:11.000-0600 | 2025-11-07T09:29:36.000-0600
DTVIEWER-19857 | Unable to update midtier gg password | null | 724Access Replication Management 2025.04 | N/A | Defect | Medium |  |  | null | Botta, Venkata Satya Prasanth Kumar | Open | null | null | null | 2025-11-05T03:37:38.000-0600 |  | DTVIEWER-19648, DTVIEWER-19868
DTVIEWER-19856 | Enhance the logical domain VRs to check for Blood bank scenarios | null | N/A | N/A | Task | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-05T03:27:34.000-0600 |  | DTVIEWER-19855
DTVIEWER-19855 | Add search and display capabilities for MRN/FIN in Blood bank all facility device | null | N/A | N/A | Story | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-05T03:25:26.000-0600 |  | DTVIEWER-18664, DTVIEWER-19856
DTVIEWER-19854 | Replicate all encounter data for Blood bank all facilities device | null | N/A | N/A | Story | Medium |  |  | null | Datta, Saikat | In Review | null | null | null | 2025-11-05T03:23:26.000-0600 |  | DTVIEWER-18664
DTVIEWER-19853 | Add logical domain id column for Blood bank tables in MT | null | N/A | N/A | Story | Medium |  |  | null | Datta, Saikat | In Review | null | null | null | 2025-11-05T03:21:44.000-0600 |  | DTVIEWER-18664
DTVIEWER-19852 | Package Access Request for 673494 from AZSL_BE | null | N/A | 724Access Downtime Viewer 5.16.3 | Issue Investigation | Medium |  | 23.0 days | null | Gummala, Sruthi Reddy | Waiting for Reporter Input | null | null | null | 2025-11-05T01:49:43.000-0600
DTVIEWER-19851 | (Existing) Console logs not updated while PC upgrade trigerred for OCI admin tool | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-05T01:18:46.000-0600 | 2025-11-06T00:32:51.000-0600 | DTVIEWER-19752
DTVIEWER-19850 | Login window text misaligned | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Critical |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-04T12:52:42.000-0600 | 2025-11-05T15:15:49.000-0600
DTVIEWER-19849 | Login window text misaligned | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Critical |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-11-04T12:46:35.000-0600 | 2025-11-05T15:14:48.000-0600
DTVIEWER-19848 | Monitoring not being pushed at end of mt_upgrade.ksh | null | 724Access Replication Management 2025.02 | N/A | Issue Investigation | Medium |  | 14.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-04T11:55:51.000-0600 | 2025-11-25T10:23:12.000-0600 | DTVIEWER-19839
DTVIEWER-19847 | ADVN_MD Monitoring tables need purge | null | 724Access Replication Management - None | N/A | Issue Investigation | Medium |  | 0.0 days | null | Gaskell, Robin | Closed | null | null | null | 2025-11-04T10:33:53.000-0600 | 2025-11-04T12:51:27.000-0600
DTVIEWER-19846 | Inquiry Regarding Future Date Limitations in MAR Printing via 724 Access Viewer | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 1.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-11-04T09:01:37.000-0600 | 2025-11-05T14:37:23.000-0600
DTVIEWER-19845 | 724DTV Security Non-Required | null | N/A | N/A | Feature | Medium |  |  | null |  | Closed | null | null | null | 2025-11-03T16:10:14.000-0600 | 2025-11-03T16:13:01.000-0600
DTVIEWER-19844 | Removing SITHS card from 724DTV does not logout user | null | N/A | 724Access Downtime Viewer 5.16.3 | Issue Investigation | Medium |  | 3.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-11-03T09:51:33.000-0600 | 2025-11-07T05:13:05.000-0600 | DTVIEWER-19876
DTVIEWER-19843 | Calendar navigation icons lack accessible names WCAG 1.1.1 | null | N/A | 724Access Ambulatory Viewer 1.4 | Defect | Medium |  |  | null |  | Closed | null | null | null | 2025-11-03T07:09:16.000-0600 | 2025-11-03T08:54:56.000-0600
DTVIEWER-19842 | Calendar navigation icons lack accessible names WCAG 1.1.1 | null | N/A | 724Access Ambulatory Viewer 1.4 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-03T07:08:21.000-0600
DTVIEWER-19841 | Section 503.2 – Partial failure to support platform accessibility settings | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-03T06:44:35.000-0600
DTVIEWER-19840 | WCAG 4.1.3 – Status messages not announced by screen reader (JAWS) | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | Medium |  |  | null |  | Submitted | null | null | null | 2025-11-03T06:00:32.000-0600
DTVIEWER-19839 | MCLA_MI monitoring jar push due to lots of ssh alerts | null | 724Access Replication Management 2025.01.01 | N/A | Issue Investigation | Medium |  | 2.0 days | null | Gaskell, Robin | Closed | null | null | null | 2025-11-03T04:38:02.000-0600 | 2025-11-05T12:10:16.000-0600 | DTVIEWER-18301, DTVIEWER-19848
DTVIEWER-19838 | (non-issue) During silent install /log option is not working and not creating any log file | null | N/A | 724Access Ambulatory Viewer 1.4.1 | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-03T00:28:39.000-0600 | 2025-11-04T04:59:28.000-0600
DTVIEWER-19837 | After removing authorized_keys file silent installation is not erroring out as 308 it is erroring out as 5 error code | null | N/A | N/A | Task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-11-03T00:24:35.000-0600 | 2025-11-05T01:03:18.000-0600
DTVIEWER-19834 | 462466828 CCH_CD Package Access Request for 650541 | null | N/A | 724Access Downtime Viewer 5.15.1 | Issue Investigation | Medium |  | 1.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-10-31T08:46:01.000-0500 | 2025-11-03T09:24:26.000-0600
DTVIEWER-19833 | Olympus monitoring not working for device | null | 724Access Replication Management 2025.02.02 | N/A | Issue Investigation | Medium |  | 3.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-31T06:33:30.000-0500 | 2025-11-05T07:57:24.000-0600
DTVIEWER-19832 | Issue with openSSH install during 5.16.2 DTV installation | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 12.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-31T02:48:21.000-0500 | 2025-11-18T08:13:13.000-0600
DTVIEWER-19828 | MASE_UK - Package Access Request for 665947 | null | N/A | 724Access Downtime Viewer 5.18.1 | Issue Investigation | Medium |  | 4.0 days | null | Rucker, Shaun | Closed | null | null | null | 2025-10-30T13:33:27.000-0500 | 2025-11-05T15:17:36.000-0600 | DTVIEWER-19565
DTVIEWER-19825 | User not locked when closing viewer — session remains active causing security risk | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | High |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-30T12:53:55.000-0500 | 2025-11-05T15:16:57.000-0600
DTVIEWER-19824 | Create a VR for session management both downtime and uptime | null | N/A | N/A | Task | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-30T12:49:45.000-0500 | 2025-11-05T09:00:49.000-0600
DTVIEWER-19823 | Update help pages with session management both downtime and uptime | null | N/A | N/A | Task | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-30T12:48:53.000-0500 | 2025-11-05T09:00:28.000-0600
DTVIEWER-19822 | SSO Session Timeout Countdown and User Activity Post Not Working | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-30T12:21:17.000-0500 | 2025-11-05T15:19:56.000-0600
DTVIEWER-19821 | Backend setup fails with asking to run Run /atg/dr/724dtv/v5.4/sql/create_user_OCI.sql as SYSDBA | null | N/A | 724Access Replication Managemen 2025.02.01 | Issue Investigation | Medium |  | 9.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-30T12:04:23.000-0500 | 2025-11-12T14:04:35.000-0600
DTVIEWER-19817 | SMRC_QA: Insecure File Permission on ggs | null | N/A | 724Access Downtime Viewer 5.15 | Issue Investigation | Medium |  | 5.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-30T05:18:09.000-0500 | 2025-11-06T07:58:03.000-0600 | DTVIEWER-19424
DTVIEWER-19814 | EAST_ME NED Inconsistency on all devices post NEDLOAD | null | N/A | 724Access Ambulatory Viewer 1.4 | Issue Investigation | Medium |  | 18.0 days | null | Bhansali, Pranjal | Closed | null | null | null | 2025-10-29T10:59:22.000-0500 | 2025-11-25T03:21:19.000-0600 | DTVIEWER-19929, DTVIEWER-19465
DTVIEWER-19803 | VM Firewall Delay Causing IAM Timeout | null | N/A | 724Access Downtime Viewer 5.18.OCI | Issue Investigation | Medium |  | 10.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-28T13:40:36.000-0500 | 2025-11-12T11:17:55.000-0600 | DTVIEWER-19802
DTVIEWER-19802 | VM Firewall Delay Causing IAM Timeout | null | N/A | 724Access Downtime Viewer 5.18.OCI | Issue Investigation | Medium |  | 5.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-28T13:37:20.000-0500 | 2025-11-05T09:08:12.000-0600 | DTVIEWER-19803
DTVIEWER-19801 | Token Not Generated When Logging in Immediately After Closing Application | null | N/A | 724Access Downtime Viewer 5.18.OCI | Issue Investigation | Medium | DTVIEWER-19900 | 10.0 days | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-28T13:33:54.000-0500 | 2025-11-12T11:14:48.000-0600
DTVIEWER-19796 | unable to remove patients with Length of Stay (LOS) > 48hrs in DTV ED Tracking board | null | N/A | 724Access Downtime Viewer 5.15.1 | Issue Investigation | Medium |  | 19.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-28T00:33:57.000-0500 | 2025-11-24T02:16:11.000-0600
DTVIEWER-19793 | mt_upgrade/mt_setup doesn't enable stats job | null | 724Access Replication Management 2025.02.02 | N/A | Issue Investigation | Medium |  | 7.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-27T04:41:25.000-0500 | 2025-11-05T12:22:57.000-0600 | DTVIEWER-19863
DTVIEWER-19787 | Purge script running well into the next day | null | N/A | 724Access Downtime Viewer 5.16.1 | Issue Investigation | Medium |  | 19.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-10-24T09:35:03.000-0500 | 2025-11-21T07:57:58.000-0600 | DTVIEWER-19749
DTVIEWER-19784 | (Cannot reproduce) While adding new device, save button is disabled sometimes | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | High |  |  | null | Nagaraju, Priyanka | Closed | null | null | null | 2025-10-24T03:08:56.000-0500 | 2025-11-04T09:15:55.000-0600 | DTVIEWER-19768
DTVIEWER-19782 | DTV is not loading after upgrading to 5.18 | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | Medium |  | 17.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-23T22:04:04.000-0500 | 2025-11-18T02:59:33.000-0600 | DTVIEWER-19830
DTVIEWER-19781 | 724Access Install Issues (USAL_AL) | null | N/A | 724Access Ambulatory Viewer 1.3 | Issue Investigation | Medium |  | 14.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-23T17:10:48.000-0500 | 2025-11-12T23:51:14.000-0600
DTVIEWER-19773 | QEMR_AU: Intake and Output volume is not matching with the Millennium. | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 12.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-23T11:19:50.000-0500 | 2025-11-11T06:57:50.000-0600
DTVIEWER-19763 | 5.18 upgrader failing with Unable to copy secure definitions | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | High |  | 14.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-21T15:26:09.000-0500 | 2025-11-11T03:29:12.000-0600
DTVIEWER-19752 | (Non-issue) Getting error while upgrading the device | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-10-20T07:02:10.000-0500 | 2025-11-05T01:20:45.000-0600 | DTVIEWER-19851
DTVIEWER-19743 | 724Access DTV Reference Pages - Maintain section | null | N/A | 724Access Downtime Viewer - None | Story | Medium |  |  | null |  | Closed | null | null | null | 2025-10-16T18:24:16.000-0500 | 2025-11-19T22:15:00.000-0600
DTVIEWER-19742 | 724Access Ambulatory Viewer DB and OS Compatibility Matrix | null | 724Access Replication Management - None | N/A | Story | Medium |  |  | null | Rucker, Shaun | Closed | null | null | null | 2025-10-16T18:00:55.000-0500 | 2025-11-19T22:13:47.000-0600
DTVIEWER-19741 | 724Access Ambulatory Viewer Group SSH Implementation Document | null | 724Access Replication Management - None | N/A | Story | Medium |  |  | null |  | Closed | null | null | null | 2025-10-16T16:21:26.000-0500 | 2025-11-19T22:11:30.000-0600
DTVIEWER-19740 | CAMH_CD Remote upgrade not working to 5.17.1 on 2025.02.01 toolkitin PROD | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | High |  | 19.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-16T16:16:12.000-0500 | 2025-11-13T00:52:24.000-0600
DTVIEWER-19737 | 724Access Replication Management About Me | null | 724Access Replication Management - None | N/A | Story | Medium |  |  | null |  | Closed | null | null | null | 2025-10-16T15:04:08.000-0500 | 2025-11-19T22:07:21.000-0600
DTVIEWER-19729 | During PC load status is not showing in DTV admin tool | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-16T06:33:14.000-0500 | 2025-11-13T21:44:00.000-0600
DTVIEWER-19727 | Fallbacks should be trigerred in case of both auth server and redirect server unreachability | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | High |  |  | null | Saha, Sudipta | Closed | null | null | null | 2025-10-16T03:54:01.000-0500 | 2025-11-04T04:13:11.000-0600 | DTVIEWER-19717
DTVIEWER-19723 | (Setup Issue) AMB PC Loads failed sometimes with VLOAD addition or v1 trail file creation | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | Medium |  |  | null | Botta, Venkata Satya Prasanth Kumar | Closed | null | null | null | 2025-10-16T03:50:15.000-0500 | 2025-11-17T15:17:22.000-0600
DTVIEWER-19717 | Session management to be used from DB in case of downtime scenarios | null | N/A | 724Access Downtime Viewer 5.18.OCI | Defect | High |  |  | null | Singhal, Avneesh | Closed | null | null | null | 2025-10-15T12:55:59.000-0500 | 2025-11-06T10:08:08.000-0600 | DTVIEWER-19721, DTVIEWER-19722, DTVIEWER-19724, DTVIEWER-19726, DTVIEWER-19727
DTVIEWER-19702 | HS_AL: Update OSHI/JNA version in 724monitoring.jar | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 19.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-14T11:39:19.000-0500 | 2025-11-10T23:38:26.000-0600 | DTVIEWER-18912, DTVIEWER-19794
DTVIEWER-19698 | Cover all Test Scenerios from Admintool-Modify Device | null | N/A | N/A | Story | Medium |  |  | null | Bhansali, Pranjal | Closed | null | null | null | 2025-10-14T08:34:49.000-0500 | 2025-11-04T23:41:33.000-0600
DTVIEWER-19690 | Remove dba_objects grants and references in ora_manage_user/mt_purge_cursor | null | N/A | N/A | Task | Medium |  |  | null | Sun, Chloe | Closed | null | null | null | 2025-10-13T15:30:19.000-0500 | 2025-11-13T10:29:12.000-0600 | DTVIEWER-19670
DTVIEWER-19685 | WARNING: Unable to determine password for ... user | null | 724Access Replication Management 2024.04.02.01 | N/A | Issue Investigation | Medium |  | 23.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-10-10T08:26:39.000-0500 | 2025-11-12T09:32:41.000-0600 | DTVIEWER-19976
DTVIEWER-19673 | Discover changes required for Oracle goldengate 23ai with toolkit. | null | N/A | N/A | Spike | Medium |  |  | null | Thakrar, Mihir | Issue Done | null | null | null | 2025-10-09T12:20:57.000-0500 | 2025-11-03T11:59:25.000-0600
DTVIEWER-19670 | ora_manage_user.sql insufficient privilege issue_MT_UPGRADE | null | N/A | N/A | Sub-task | Medium |  |  | null | Sun, Chloe | Closed | null | null | null | 2025-10-09T06:27:45.000-0500 | 2025-11-13T10:28:53.000-0600 | DTVIEWER-19690
DTVIEWER-19658 | New reference page for SSO | null | N/A | N/A | Story | Medium |  |  | null | Nagaraju, Priyanka | Closed | null | null | null | 2025-10-07T13:19:31.000-0500 | 2025-11-07T11:05:35.000-0600 | DTVIEWER-19606
DTVIEWER-19648 | Unable to update midtier gg password | null | N/A | N/A | Sub-task | Medium |  |  | null | Datta, Saikat | Closed | null | null | null | 2025-10-06T21:12:57.000-0500 | 2025-11-05T03:46:24.000-0600 | DTVIEWER-19857
DTVIEWER-19638 | Regenerate help pages for AMB and DTV | null | N/A | N/A | Story | Medium |  |  | null | Uppalapati, Nandita | Closed | null | null | null | 2025-10-02T14:05:21.000-0500 | 2025-11-25T13:15:23.000-0600
DTVIEWER-19636 | Modify help pages for login workflow for both AMB and DTV | null | N/A | N/A | Story | Medium |  |  | null | Uppalapati, Nandita | Closed | null | null | null | 2025-10-01T12:38:30.000-0500 | 2025-11-19T12:57:16.000-0600
DTVIEWER-19619 | test dependency version upgrade for enabling skip checks in 724-jar-reactor | null | N/A | N/A | Story | Medium |  |  | null | Avasthi, Pawas [X] | Closed | null | null | null | 2025-09-29T04:32:36.000-0500 | 2025-11-03T22:42:16.000-0600 | DTVIEWER-19589
DTVIEWER-19608 | Create PIV VRs | null | N/A | N/A | Story | Medium |  |  | null | Selvakumar, Suganya | Closed | null | null | null | 2025-09-25T16:57:48.000-0500 | 2025-11-24T14:39:39.000-0600
DTVIEWER-19603 | RESK_SE - 724: Search patient tab, column Other doesn't display å ä ö | null | N/A | 724Access Downtime Viewer 5.16.3 | Issue Investigation | Low |  | 31.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-09-25T04:04:28.000-0500 | 2025-11-07T06:27:01.000-0600 | DTVIEWER-16475, DTVIEWER-19791
DTVIEWER-19601 | MUNS_MI, Unable to Collect Audit Logs via 724Access Admin Tool | null | N/A | 724Access Downtime Viewer 5.17.1 | Issue Investigation | Medium |  | 38.0 days | null | Dhingra, Gaurav | Closed | null | null | null | 2025-09-24T12:25:24.000-0500 | 2025-11-18T03:01:18.000-0600
DTVIEWER-19585 | Create Script Prototype | null | N/A | N/A | Sub-task | Medium |  |  | null | Burgstahler, Aiden | Issue Done | null | null | null | 2025-09-19T09:45:06.000-0500 | 2025-11-19T09:40:33.000-0600
DTVIEWER-19584 | Write Technical Design Document | null | N/A | N/A | Sub-task | Medium |  |  | null | Burgstahler, Aiden | Issue Done | null | null | null | 2025-09-19T09:42:14.000-0500 | 2025-11-19T09:40:21.000-0600
DTVIEWER-19582 | Write Requirements Document | null | N/A | N/A | Sub-task | Medium |  |  | null | Burgstahler, Aiden | Issue Done | null | null | null | 2025-09-18T09:46:47.000-0500 | 2025-11-19T09:40:03.000-0600
DTVIEWER-19529 | SHCN_AU ¦¦ Non-Prod ¦¦ Reverse ssh is not working | null | N/A | 724Access Downtime Viewer 5.15.1 | Issue Investigation | Low |  | 47.0 days | null | Datta, Saikat | Closed | null | null | null | 2025-09-11T01:50:13.000-0500 | 2025-11-17T02:31:00.000-0600 | DTVIEWER-19862
DTVIEWER-19503 | PIV integration for downtime authenitication | null | N/A | N/A | Story | Medium |  |  | null | Uppalapati, Nandita | Closed | null | null | null | 2025-09-09T16:21:51.000-0500 | 2025-11-13T15:23:53.000-0600
DTVIEWER-19482 | BE_UPGRADE Failed (The DR_ENV_DEVTK file was not updated) | null | N/A | N/A | Sub-task | High |  |  | null | Datta, Saikat | Closed | null | null | null | 2025-09-08T13:15:32.000-0500 | 2025-11-18T00:08:40.000-0600
DTVIEWER-19456 | Dynamically set oracle home path - Intergration Testing | null | N/A | N/A | Sub-task | Medium |  |  | null | Datta, Saikat | Issue Done | null | null | null | 2025-09-03T10:16:03.000-0500 | 2025-11-11T11:25:42.000-0600
DTVIEWER-19373 | Dynamically set the oracle home path | null | N/A | N/A | Story | Medium |  |  | null | Datta, Saikat | Closed | null | null | null | 2025-08-21T12:06:37.000-0500 | 2025-11-18T00:21:14.000-0600 | DTVIEWER-15743, DTVIEWER-19372, DTVIEWER-15546
DTVIEWER-19293 | remove all ordered Blood work in ccd report Within the 724 Ambulatory Viewer | null | N/A | 724Access Downtime Viewer 5.18 | Issue Investigation | Medium |  | 69.0 days | null | Singla, Rahul | Closed | null | null | null | 2025-08-11T13:58:21.000-0500 | 2025-11-17T12:04:12.000-0600 | DTVIEWER-19313
DTVIEWER-19217 | KMC_HI-724 DTV OCI Redeployment Cleanup | null | 724Access Replication Management - None | N/A | Issue Investigation | Medium |  | 78.0 days | null | Botta, Venkata Satya Prasanth Kumar | Closed | null | null | null | 2025-07-30T12:16:56.000-0500 | 2025-11-18T11:14:33.000-0600 | DTVIEWER-19930
DTVIEWER-19198 | 724Access Admin Tool Location Browser Save (DTV & AMB) | null | N/A | N/A | Story | Medium |  |  | null |  | Closed | null | null | null | 2025-07-28T10:24:58.000-0500 | 2025-11-25T08:24:29.000-0600 | DTVIEWER-19192
DTVIEWER-19187 | Update 724 Toolkit documentation to add disclaimer for V500 password | null | N/A | N/A | Task | Medium |  |  | null | Bolls, Aeja | Closed | null | null | null | 2025-07-24T14:21:38.000-0500 | 2025-11-13T11:10:41.000-0600
DTVIEWER-19178 | OUH_UK Anesthetic Chart View shows one page when there are multiples | null | N/A | 724Access Downtime Viewer 5.15.1 | Issue Investigation | Medium |  | 74.0 days | null | Adhikari, Tamal | Closed | null | null | null | 2025-07-23T14:52:41.000-0500 | 2025-11-04T21:43:54.000-0600
DTVIEWER-19176 | Certain items in lab results and patient care results appear multiple times in patient records in 724AccessViewer. | null | N/A | 724Access Downtime Viewer 5.16.1 | Issue Investigation | Medium |  | 76.0 days | null | Adhikari, Tamal | Closed | null | null | null | 2025-07-23T09:23:31.000-0500 | 2025-11-07T07:24:58.000-0600
DTVIEWER-19043 | Cannot create view AMB 1.4 | null | N/A | 724Access Ambulatory Viewer 1.3 | Issue Investigation | High |  | 103.0 days | null | Adhikari, Tamal | Closed | null | null | null | 2025-06-25T05:14:15.000-0500 | 2025-11-18T00:18:09.000-0600 | DTVIEWER-18061
DTVIEWER-19040 | BHS_FL Requested for SvcD7A Password to be Encrypted during install of 5.15+ DTV | null | N/A | 724Access Downtime Viewer 5.15.2 | Issue Investigation | Medium | DTVIEWER-19902 | 101.0 days | null | Bolls, Aeja | Closed | null | null | null | 2025-06-24T11:00:15.000-0500 | 2025-11-12T11:55:15.000-0600
DTVIEWER-19034 | 724Access Ambulatory Viewer Accessibility Testing | null | N/A | N/A | Spike | Medium |  |  | null | Kumari, Maneesha | Closed | null | null | null | 2025-06-23T12:20:53.000-0500 | 2025-11-06T08:12:28.000-0600 | PCFRAME-16796, DTVIEWER-13605
DTVIEWER-18956 | Admin tool related audits Strings - Reason for accessing patient chart | null | N/A | N/A | Sub-task | High |  |  | null | Bolls, Aeja | Closed | null | null | null | 2025-05-29T09:44:12.000-0500 | 2025-11-25T06:08:58.000-0600
DTVIEWER-18954 | HAMC_QAT: Windows version not reflecting correctly in Olympus | null | N/A | 724Access Downtime Viewer 5.16.2 | Issue Investigation | Medium |  | 115.0 days | null | Sun, Chloe | Closed | null | null | null | 2025-05-29T06:56:14.000-0500 | 2025-11-06T12:35:32.000-0600 | DTVIEWER-19753
DTVIEWER-18831 | Update correct logger filename for AMB during PC Load | null | 724Access Replication Management 2024.04.02 | N/A | Defect | Medium |  |  | null | Nimbalkar, Poonam | Closed | null | null | null | 2025-04-29T01:32:10.000-0500 | 2025-11-04T12:20:04.000-0600 | DTVIEWER-18763
DTVIEWER-18571 | 724 DTV OHRM Security Bar Remediation | null | N/A | N/A | Feature | High |  |  | null | Patel, Sameena | Closed | null | null | null | 2025-03-17T04:33:29.000-0500 | 2025-11-12T12:58:21.000-0600 | DTVIEWER-18570, DTVIEWER-19106, DTVIEWER-19114, DTVIEWER-19451
DTVIEWER-18570 | Upgrade JDK 1.8 to a later version | null | N/A | N/A | Feature | High |  |  | null | Costa, Floid | Closed | null | null | null | 2025-03-17T04:19:40.000-0500 | 2025-11-03T22:45:09.000-0600 | DTVIEWER-18571
DTVIEWER-18526 | Facility Pump reloads fail with LOB issue | null | N/A | N/A | Task | Medium |  |  | null | Patel, Sameena | Closed | null | null | null | 2025-03-05T08:15:56.000-0600 | 2025-11-14T12:51:58.000-0600
DTVIEWER-18468 | RESK_SE - OpenSSH Vulnerabilities | null | N/A | 724Access Downtime Viewer 5.16.2 | Defect | High |  |  | null | Kumari, Maneesha | Issue Done | null | null | null | 2025-02-24T03:42:16.000-0600 | 2025-11-24T04:35:56.000-0600
DTVIEWER-17971 | Jenkins build is not working for 724AccessViewer | null | N/A | N/A | Story | Medium |  |  | null |  | Closed | null | null | null | 2024-10-25T03:46:07.000-0500 | 2025-11-25T08:48:35.000-0600 | DTVIEWER-17533
DTVIEWER-17821 | OWASP for seventwentyfour-viewer-osgi-springframework | null | N/A | N/A | Task | Medium |  |  | null | Wang, Frank | Closed | null | null | null | 2024-09-19T17:46:51.000-0500 | 2025-11-03T22:40:16.000-0600 | DTVIEWER-17816
DTVIEWER-17820 | OWASP for 724monitoring | null | N/A | N/A | Task | Medium |  |  | null | Wang, Frank | Closed | null | null | null | 2024-09-19T17:46:12.000-0500 | 2025-11-03T22:39:27.000-0600 | DTVIEWER-17816
DTVIEWER-17819 | OWASP for 724-mysql-upgrader | null | N/A | N/A | Task | Medium |  |  | null | Wang, Frank | Closed | null | null | null | 2024-09-19T17:45:48.000-0500 | 2025-11-03T22:38:15.000-0600 | DTVIEWER-17816
DTVIEWER-17818 | OWASP for 724-db-config | null | N/A | N/A | Task | Medium |  |  | null | Wang, Frank | Closed | null | null | null | 2024-09-19T17:45:18.000-0500 | 2025-11-03T22:36:27.000-0600 | DTVIEWER-17816
DTVIEWER-17817 | OWASP for 724-alerting | null | N/A | N/A | Task | Medium |  |  | null | Wang, Frank | Closed | null | null | null | 2024-09-19T17:44:51.000-0500 | 2025-11-03T22:35:24.000-0600 | DTVIEWER-17816
DTVIEWER-17816 | Addressing OWASP Dependency Checker Concerns | null | N/A | N/A | Story | Medium |  |  | null | Wali, Amitkumar | Closed | null | null | null | 2024-09-19T17:39:54.000-0500 | 2025-11-03T22:40:41.000-0600 | DTVIEWER-17810, DTVIEWER-17817, DTVIEWER-17818, DTVIEWER-17819, DTVIEWER-17820, DTVIEWER-17821
DTVIEWER-15479 | Project Review | null | N/A | N/A | Sub-task | Medium |  |  | null | Joy, A Anline [X] | Closed | null | null | null | 2023-11-07T09:59:24.000-0600 | 2025-11-25T08:59:24.000-0600
DTVIEWER-15478 | Documentation | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:23.000-0600 | 2025-11-25T08:59:22.000-0600
DTVIEWER-15477 | Engineering Testing | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:23.000-0600 | 2025-11-25T08:59:21.000-0600
DTVIEWER-15476 | Test Script | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:22.000-0600 | 2025-11-25T08:59:22.000-0600
DTVIEWER-15475 | Code | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:21.000-0600 | 2025-11-25T08:59:23.000-0600
DTVIEWER-15474 | Design | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:20.000-0600 | 2025-11-25T08:59:23.000-0600
DTVIEWER-15473 | Requirement and Hazard | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:20.000-0600 | 2025-11-25T08:59:24.000-0600
DTVIEWER-15472 | Project Kickoff | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:19.000-0600 | 2025-11-25T08:59:23.000-0600
DTVIEWER-15470 | Project Review | null | N/A | N/A | Sub-task | Medium |  |  | null | Joy, A Anline [X] | Closed | null | null | null | 2023-11-07T09:59:16.000-0600 | 2025-11-25T08:56:50.000-0600
DTVIEWER-15469 | Documentation | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:15.000-0600 | 2025-11-25T08:56:47.000-0600
DTVIEWER-15468 | Engineering Testing | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:14.000-0600 | 2025-11-25T08:56:50.000-0600
DTVIEWER-15467 | Test Script | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:14.000-0600 | 2025-11-25T08:56:48.000-0600
DTVIEWER-15466 | Code | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:13.000-0600 | 2025-11-25T08:56:48.000-0600
DTVIEWER-15465 | Design | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:12.000-0600 | 2025-11-25T08:56:47.000-0600
DTVIEWER-15464 | Requirement and Hazard | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:12.000-0600 | 2025-11-25T08:56:48.000-0600
DTVIEWER-15463 | Project Kickoff | null | N/A | N/A | Sub-task | Medium |  |  | null | Saha, Sudipta | Closed | null | null | null | 2023-11-07T09:59:11.000-0600 | 2025-11-25T08:56:49.000-0600
DTVIEWER-15461 | Intial Analysis and Documentation | null | N/A | N/A | Sub-task | Medium |  |  | null | Costa, Floid | Closed | null | null | null | 2023-11-07T09:59:08.000-0600 | 2025-11-25T09:01:39.000-0600
DTVIEWER-15459 | Initial Analysis and Documentation | null | N/A | N/A | Sub-task | Medium |  |  | null | Mishra, Chandan [X] | Closed | null | null | null | 2023-11-07T09:59:06.000-0600 | 2025-11-25T09:01:59.000-0600
DTVIEWER-15454 | 724Access Admin Tool Security | null | N/A | N/A | Feature | Medium |  |  | null |  | Closed | null | null | null | 2023-11-07T09:15:54.000-0600 | 2025-11-03T12:06:32.000-0600 | DTVIEWER-13793
DTVIEWER-14884 | Identified DTV Vulnerabilities - Moderate Severity | null | N/A | N/A | Feature | Medium |  |  | null | Kumari, Maneesha | Closed | null | null | null | 2023-08-15T08:24:38.000-0500 | 2025-11-03T11:47:57.000-0600 | DTVIEWER-13762
DTVIEWER-12625 | 724Access Admin Tool Audit | null | N/A | N/A | Feature | Medium |  |  | null | Bolls, Aeja | Closed | null | null | null | 2022-03-10T15:27:03.000-0600 | 2025-11-03T12:05:05.000-0600 | DTVIEWER-13793